## PRD - User Stories
ID | Persona | Feature Area | User Story | Feature | Priority (MoSCoW) | Build Phase | Acceptance Criteria | Gap Filled? | Surface | Build plan phase (v2) | Design boards | Change note (1 Oct)
1 | Artist | Auth & Profile | As an artist, I want to register and be verified as an artist, so that I can access artist-only features. | Register | Must | Phase 2 | Registration form collects name/email/genre; account flagged as artist role; cannot access artist dashboard until verified. | Gap | Native, web | 3 Artist and live pipeline | ArtistOnboarding, Profile-Owner, AccountSettings
2 | Artist | Auth & Profile | As an artist, I want to log in and log out of my profile. | Log in / Log out | Must | Phase 2 | Valid credentials grant session; logout clears session; invalid credentials show clear error. |  | Native, web | 3 Artist and live pipeline | ArtistOnboarding, Profile-Owner, AccountSettings
3 | Artist | Auth & Profile | As an artist, I want to view my profile, so that I can see how fans see me. | See profile | Must | Phase 2 | Profile shows bio, photo, clips, stats exactly as a fan would view it. |  | Native, web | 3 Artist and live pipeline | ArtistOnboarding, Profile-Owner, AccountSettings
4 | Artist | Auth & Profile | As an artist, I want to edit my profile, so that my public information stays current. | Edit profile | Must | Phase 2 | All editable fields save and reflect immediately on the public profile. |  | Native, web | 3 Artist and live pipeline | ArtistOnboarding, Profile-Owner, AccountSettings
5 | Artist | Auth & Profile | As an artist, I want password-protected profile edits, so that unauthorized changes can't happen. | Edit profile | Should | Phase 2 | Any profile edit requires re-entering password before saving. |  | Native, web | 3 Artist and live pipeline | ArtistOnboarding, Profile-Owner, AccountSettings
6 | Artist | Auth & Profile | As an artist, I want the option of 2FA on any profile edits, so that my account is harder to compromise. | Edit profile | Could | Phase 3 | 2FA can be enabled/disabled in settings; when on, edits require a second factor. |  | Native, web | 3 Artist and live pipeline | ArtistOnboarding, Profile-Owner, AccountSettings
7 | Artist | Auth & Profile | As an artist, I want to close my account, so that I can leave the platform if I choose. | Close account | Should | Phase 2 | Closing account requires confirmation; content handling policy (deleted/archived) is disclosed before confirming. |  | Native, web | 6 Hardening | ArtistOnboarding, Profile-Owner, AccountSettings
8 | Artist | Auth & Profile | As an artist, I want to request access to data held about me, so that I can exercise my data rights. | Request data | Should | Phase 2 | Request generates a data export or a tracked request ticket within a stated turnaround time. |  | Native, web | 6 Hardening | ArtistOnboarding, Profile-Owner, AccountSettings
9 | Artist | Live Performance - Solo/Versus | As an artist, I want to choose between a solo show or a versus show, so that I can pick the format that fits my performance. | Perform Solo / Perform Versus | Must | Pilot | Join flow offers Solo and Versus as the first choice; layout adapts accordingly. |  | Native, web | 3 Artist and live pipeline | Create, Schedule, Countdown, Console
10 | Artist | Live Performance - Solo/Versus | As an artist, I want to go live, so that fans can watch my performance in real time. | Go live | Must | Pilot | Artist can start a session; video/audio publish successfully; viewers can join and see/hear the stream. |  | Native, web | 3 Artist and live pipeline | Create, Schedule, Countdown, Console | Row superseded in part: shows are booked at least 30 minutes ahead, with no unscheduled go-live.
11 | Artist | Live Performance - Solo/Versus | As an artist, I want to consent to my show being recorded before it happens, so that I control whether a recording is kept. | Consent to Recording | Should | Phase 2 | A consent toggle/prompt appears before going live; recording only starts if consent is given. | Gap | Native, web | 3 Artist and live pipeline | Create, Schedule, Countdown, Console | Check against architecture: recordings are the product (contract basis), so a pre-show recording consent prompt may not be needed. Needs decision.
12 | Artist | Multi-Camera & Production | As an artist, I want to sync 2-4 camera feeds in real time, so that I can offer multiple shots for my live video. | Automate Content director / Control content direction | Should | Phase 2 | 2-4 devices can join as camera feeds tagged to the artist; all publish video successfully to the same room. |  | Native, web | 3 Artist and live pipeline | CameraSettings, DirectionSettings, DevicesSettings, CameraMode, KitCheck | One feed per physical device. See 'Pair a camera'.
13 | Artist | Multi-Camera & Production | As an artist, I want to select the one shot my viewers see at a time, so that they don't see all shots at once. | Control content direction | Should | Phase 2 | Director panel lets artist tap one feed as 'active'; all viewers see only that feed within 1 second of the switch. |  | Native, web | 3 Artist and live pipeline | CameraSettings, DirectionSettings, DevicesSettings, CameraMode, KitCheck
14 | Artist | Multi-Camera & Production | As an artist, I want wide, medium, close, and extreme close-up shots, so that I have more angle options. | Control content direction | Could | Phase 3 | Each camera feed can be labeled by shot type; label displays in the director panel. |  | Native, web | 3 Artist and live pipeline | CameraSettings, DirectionSettings, DevicesSettings, CameraMode, KitCheck
15 | Artist | Multi-Camera & Production | As an artist, I want moving zoom shots, so that my videos have varied angles. | Control content direction | Should | Phase 2 | Moving zoom is a real per-camera setting that uses the lens, never a digital crop, with a duration (2s, 4s, 8s or custom). The artist switches it on or off. | Updated 1 Oct | Native, web | 3 Artist and live pipeline | CameraSettings, DirectionSettings, DevicesSettings, CameraMode, KitCheck | Was 'smooth digital zoom', Could, Future Roadmap. Decided 30 Sept: lens zoom only, both moving zoom and pan are real settings.
16 | Artist | Multi-Camera & Production | As an artist, I want slight object-pan shots that never lose the main subject, so that my videos feel alive. | Control content direction | Should | Phase 2 | Pan is a per-camera setting inside the zoom ceiling, with a duration (2s, 4s, 8s or custom), off by default. It keeps the subject within frame bounds at all times. | Updated 1 Oct | Native, web | 3 Artist and live pipeline | CameraSettings, DirectionSettings, DevicesSettings, CameraMode, KitCheck | Was Could, Future Roadmap. Decided 30 Sept.
17 | Artist | Multi-Camera & Production | As an artist, I want an automated director that alternates shots for me, so that I don't have to switch manually. | Automate Content director | Must | Pilot | Auto director is on by default. It cycles between feeds using only the moves the artist has switched on, and the artist can review the rule set before enabling. | Updated 1 Oct | Native, web | 3 Artist and live pipeline | CameraSettings, DirectionSettings, DevicesSettings, CameraMode, KitCheck | Was Won't now. Built and pilot-tested (AI director, shot grammar unchanged).
18 | Artist | Multi-Camera & Production | As an artist, I want shot choices to reflect the emotional moment of the performance. | Automate Content director | Won't now | Future Roadmap | Auto-director's shot selection correlates with defined audio/performance signals in at least a documented test set. |  | Native, web | 3 Artist and live pipeline | CameraSettings, DirectionSettings, DevicesSettings, CameraMode, KitCheck
19 | Artist | Multi-Camera & Production | As an artist, I want to decide when the auto-director kicks in, so that I keep manual control while engaging with viewers. | Control content direction | Should | Phase 2 | Auto-director has an explicit on/off toggle, on by default. The manual cuts panel is closed by default on the live console. | Updated 1 Oct | Native, web | 3 Artist and live pipeline | CameraSettings, DirectionSettings, DevicesSettings, CameraMode, KitCheck | Was 'defaulting to off'. Decided: on by default.
20 | Artist | Multi-Camera & Production | As an artist, I want accentuated cuts aligned to staccato performance moments, so that my show feels production-grade. | Automate Content director | Won't now | Future Roadmap | Documented rule set ties cut timing to defined audio transients in a test recording. |  | Native, web | 3 Artist and live pipeline | CameraSettings, DirectionSettings, DevicesSettings, CameraMode, KitCheck
21 | Artist | Engagement | As an artist, I want to send stickers to a live show, so that I can show my engagement with viewers. | Send Stickers | Won't now | Future Roadmap | REJECTED per confirmed decision: artists use the comments panel (text + standard emoji), not the sticker bar. Sticker bar is fan-only. Row kept for decision traceability, not for build. | Rejected (Decision) | Native, web | 3 Artist and live pipeline | Show, YT-Show, Inbox, Thread | Still rejected. Support (tokens) is the viewer-to-artist gesture; artists use comments.
22 | Artist | Engagement | As an artist, I want to pick someone from the live audience to speak with, so that I can drive fan engagement. | Host Fan Live | Should | Phase 2 | Artist can select a connected viewer; selected viewer receives an invite they can accept or decline. |  | Native, web | 3 Artist and live pipeline | Show, YT-Show, Inbox, Thread
23 | Artist | Engagement | As an artist, I want to comment on my own performances. | Send comments | Must | Pilot | Artist can post a comment visible to all viewers on the current show. |  | Native, web | 3 Artist and live pipeline | Show, YT-Show, Inbox, Thread
24 | Artist | Engagement | As an artist, I want to reply to comments. | Reply Comments | Must | Pilot | Reply shows an arrow + indentation under the original comment, visible to all. |  | Native, web | 3 Artist and live pipeline | Show, YT-Show, Inbox, Thread
25 | Artist | Engagement | As an artist, I want to quote comments. | Quote Comments | Must | Pilot | Quoted text renders in blue with quotation marks above the new comment, visible to all. |  | Native, web | 3 Artist and live pipeline | Show, YT-Show, Inbox, Thread
26 | Artist | Engagement | As an artist, I want to like my own performances. | Like content | Should | Phase 2 | Like button available on own recorded/live content; count updates for all viewers. |  | Native, web | 3 Artist and live pipeline | Show, YT-Show, Inbox, Thread
27 | Artist | Engagement | As an artist, I want to follow a fan or another artist. | Follow artist | Should | Phase 2 | Follow action updates the followed user's follower count and appears in artist's following list. |  | Native, web | 3 Artist and live pipeline | Show, YT-Show, Inbox, Thread
28 | Artist | Engagement | As an artist, I want to behave as a fan when relating to other artists, so that I can support peers the same way any fan would. | Send Stickers / Vote artist | Could | Phase 3 | Artist account can send stickers/votes/comments on another artist's show identically to a fan account. |  | Native, web | 3 Artist and live pipeline | Show, YT-Show, Inbox, Thread
29 | Artist | Competitions & Collaboration | As an artist, I want to enter competitions by genre, so that I can grow my fan base. | Enter competitions | Should | Phase 2 | Artist can browse open competitions filtered by genre and submit entry before the stated deadline. |  | Native, web | Post-launch | Competitions, CompetitionDetail, VersusInvite | Competitions are mock only today; Post-launch.
30 | Artist | Competitions & Collaboration | As an artist, I want to collaborate with other artists on curated live content, so that we grow audiences through variety and network effects. | Perform Versus | Could | Phase 3 | Two or more artists can be linked to a single scheduled show, all appearing on relevant profiles. |  | Native, web | 3 Artist and live pipeline | Competitions, CompetitionDetail, VersusInvite
31 | Artist | Content & Sharing | As an artist, I want to see my recorded performances. | Watch recorded show | Should | Phase 2 | Recorded shows list on artist dashboard with playback. |  | Native, web | 3 Artist and live pipeline | Recording, ClipEditor, Profile-Owner
32 | Artist | Content & Sharing | As an artist, I want to share snippets of my live performances to other platforms, so that I can reach new fans. | Share recorded snippets | Should | Phase 2 | Snippet generates a shareable link with dynamic preview image/title/description. |  | Native, web | 3 Artist and live pipeline | Recording, ClipEditor, Profile-Owner
33 | Artist | Financial | As an artist, I want to see my earnings per period. | See Artist Financials | Should | Phase 2 | Earnings dashboard breaks down totals by day/week/month. |  | Native, web | 3 Artist and live pipeline | WalletPayouts, WebEarnings, WebIdentity
34 | Artist | Financial | As an artist, I want to see a table of engaged fans and their support (paid and unpaid), so that I understand who supports me. | See Artist Financials | Should | Phase 2 | Table lists fan name, support type, amount (if paid), and date, sortable. |  | Native, web | 3 Artist and live pipeline | WalletPayouts, WebEarnings, WebIdentity
35 | Artist | Financial | As an artist, I want to withdraw my earnings to a payout method. | See Artist Financials | Should | Phase 2 | Artist can add a payout method and request withdrawal; status is trackable. | Gap | Native, web | 3 Artist and live pipeline | WalletPayouts, WebEarnings, WebIdentity
36 | Artist | Analytics & Ranking | As an artist, I want to see analytics on my content. | See artists Chart | Should | Phase 2 | Dashboard shows views, engagement rate, and reaction breakdown per show. |  | Native, web | 3 Artist and live pipeline | Insights
37 | Artist | Analytics & Ranking | As an artist, I want to see my ranking amongst other artists in my genre. | See artist ranking | Could | Phase 3 | Ranking updates on a defined cadence and is visible on the artist's own dashboard. |  | Native, web | Post-launch | Insights
38 | Artist | IP Protection | As an artist, I want a certificate confirming I performed a song first, with timestamps, so that my origination is protected. | Get performed it first certificate | Could | Phase 3 | Certificate is generated automatically at first performance, timestamped, and downloadable/shareable. |  | Native, web | Post-launch | Not designed
39 | Artist | IP Protection | As an artist, I want to dispute a suspected IP infringement of my certified performance. | Get performed it first certificate | Could | Future Roadmap | Artist can flag another piece of content referencing their certificate; admin receives the dispute for review. | Gap | Native, web | Post-launch | Not designed
40 | Artist | Trust & Safety | As an artist, I want to report a user or piece of content, so that abusive behavior can be reviewed. | Censor Content | Should | Phase 2 | Report submits a ticket with reason and reference to admin queue. | Gap | Native, web | 6 Hardening | Show, YT-Show, PrivacySettings, BlockedWords
41 | Artist | Trust & Safety | As an artist, I want to block a specific user, so that they can't message or comment on my content. | Blocklist User | Should | Phase 2 | Blocked user's comments/messages to this artist are hidden from the artist; blocked user is not notified. | Gap | Native, web | 6 Hardening | Show, YT-Show, PrivacySettings, BlockedWords
42 | Viewer | Auth & Profile | As a viewer, I want to create an account, so that I can use the platform's features. | Log in | Must | Phase 2 | Registration form collects name/email; account created and logged in on success. | Gap | Native, web | 2 Viewer (web) | SignUp, Login, ViewerProfile, AccountSettings
43 | Viewer | Auth & Profile | As a viewer, I want to log in and log out. | Log in / Log out | Must | Phase 2 | Valid credentials grant session; logout clears session. |  | Native, web | 2 Viewer (web) | SignUp, Login, ViewerProfile, AccountSettings
44 | Viewer | Auth & Profile | As a viewer, I want to see my own profile. | See profile | Must | Phase 2 | Profile page shows genre preferences, top artists, and basic info. |  | Native, web | 2 Viewer (web) | SignUp, Login, ViewerProfile, AccountSettings
45 | Viewer | Auth & Profile | As a viewer, I want to edit my profile. | Edit profile | Must | Phase 2 | Edits save and reflect immediately. |  | Native, web | 2 Viewer (web) | SignUp, Login, ViewerProfile, AccountSettings
46 | Viewer | Auth & Profile | As a viewer, I want password-protected profile edits. | Edit profile | Should | Phase 2 | Edits require re-entering password. |  | Native, web | 2 Viewer (web) | SignUp, Login, ViewerProfile, AccountSettings
47 | Viewer | Auth & Profile | As a viewer, I want the option of 2FA on profile edits. | Edit profile | Could | Phase 3 | 2FA can be toggled on; when on, edits require a second factor. |  | Native, web | 2 Viewer (web) | SignUp, Login, ViewerProfile, AccountSettings
48 | Viewer | Auth & Profile | As a viewer, I want to close my account. | Close account | Should | Phase 2 | Closing requires confirmation and discloses data handling. | Gap | Native, web | 6 Hardening | SignUp, Login, ViewerProfile, AccountSettings
49 | Viewer | Auth & Profile | As a viewer, I want to request access to data held about me. | Request data | Should | Phase 2 | Request generates export or tracked ticket within a stated turnaround. | Gap | Native, web | 6 Hardening | SignUp, Login, ViewerProfile, AccountSettings
50 | Viewer | Viewing Experience | As a viewer, I want to see clear video of the artist I'm watching, so that I can enjoy their performance. | Watch Live competitions | Must | Pilot | Stream displays at acceptable quality with no more than brief, rare buffering under normal network conditions. |  | Native, web | 2 Viewer (web) | Main, Live, Show, YT-Show, Recording, Search, SearchResults | Under YouTube delivery the picture quality and buffering are YouTube's. Our half is the composed picture reaching YouTube (see Reliability).
51 | Viewer | Viewing Experience | As a viewer, I want to watch recorded performances after they go live. | Watch recorded show | Should | Phase 2 | Recorded show appears in a library shortly after the live session ends and plays back correctly. |  | Native, web | 2 Viewer (web) | Main, Live, Show, YT-Show, Recording, Search, SearchResults
52 | Viewer | Viewing Experience | As a viewer, I want to discover artists by genre, name, or trending shows, so that I can find performances I'll enjoy. | See Live Competitions | Should | Phase 2 | Search/browse returns relevant results filterable by genre. | Gap | Native, web | 2 Viewer (web) | Main, Live, Show, YT-Show, Recording, Search, SearchResults
53 | Viewer | Engagement | As a viewer, I want to post messages and emojis everyone sees during a live session, so that I can engage. | Send comments / Send Emogis | Must | Pilot | Comment with emoji broadcasts to all participants in the room in real time. |  | Native, web | 2 Viewer (web) | Show, YT-Show, Inbox, Thread, SupportSheet
54 | Viewer | Engagement | As a viewer, I want to send stickers to the live show, so that I can show my engagement. | Send Stickers | Must | Pilot | Sticker animates locally and broadcasts to all other participants. |  | Native, web | 2 Viewer (web) | Show, YT-Show, Inbox, Thread, SupportSheet | Needs decision: designs use Support (tokens) and a reactions tab (design on hold), not stickers.
55 | Viewer | Engagement | As a viewer, I want to like an artist's performance. | Like content | Should | Phase 2 | Like button available on live and recorded content; count updates. |  | Native, web | 2 Viewer (web) | Show, YT-Show, Inbox, Thread, SupportSheet
56 | Viewer | Engagement | As a viewer, I want to reply to comments. | Reply Comments | Must | Pilot | Reply shows arrow + indentation, visible to all. |  | Native, web | 2 Viewer (web) | Show, YT-Show, Inbox, Thread, SupportSheet
57 | Viewer | Engagement | As a viewer, I want to quote comments. | Quote Comments | Must | Pilot | Quoted text renders in blue with quotation marks, visible to all. |  | Native, web | 2 Viewer (web) | Show, YT-Show, Inbox, Thread, SupportSheet
58 | Viewer | Engagement | As a viewer, I want to follow artists. | Follow artist | Should | Phase 2 | Follow updates artist's follower count and viewer's following list. |  | Native, web | 2 Viewer (web) | Show, YT-Show, Inbox, Thread, SupportSheet
59 | Viewer | Engagement | As a viewer, I want to be notified when a followed artist goes live or replies to my comment. | Send Message | Should | Phase 2 | Notification is delivered in-app (and/or push) within a short delay of the triggering event. | Gap | Native, web | 2 Viewer (web) | Show, YT-Show, Inbox, Thread, SupportSheet
60 | Viewer | Engagement | As a viewer, I want to accept or decline an artist's invitation to speak live on their show. | Host Fan Live | Should | Phase 2 | Viewer receives an invite prompt with accept/decline; declining does not disrupt the show. | Gap | Native, web | 2 Viewer (web) | Show, YT-Show, Inbox, Thread, SupportSheet
61 | Viewer | Financial Support | As a viewer, I want to financially support any artist. | Buy token / Vote artist | Should | Phase 2 | Viewer can complete a support transaction and see confirmation. |  | Native, web | 2 Viewer (web) | SupportSheet, Wallet, WebBuyTokens | Web only. See 'Support with tokens' and 'Wallet and token purchase'.
62 | Viewer | Financial Support | As a viewer, I want to purchase tokens for powered votes and gift tokens for artists. | Buy token / Power vote artist | Should | Phase 2 | Token purchase completes via a payment provider and balance updates immediately. |  | Native, web | 2 Viewer (web) | SupportSheet, Wallet, WebBuyTokens | Web only. Payment provider not chosen.
63 | Viewer | Financial Support | As a viewer, I want to see a breakdown of paid and unpaid support I've given to artists. | See artist Financials | Could | Phase 3 | History view lists each support action with type and amount if paid. |  | Native, web | 2 Viewer (web) | SupportSheet, Wallet, WebBuyTokens
64 | Viewer | Content & Sharing | As a viewer, I want to share an artist's live content to other platforms, so that I can generate reach for them. | Share live shows | Should | Phase 2 | Share generates a link with dynamic preview image/title/description. |  | Native, web | 2 Viewer (web) | Profile-Public, WebShowPage, Thread
65 | Viewer | Content & Sharing | As a viewer, I want to share snippets of a performance to other platforms. | Share recorded snippets | Should | Phase 2 | Snippet share generates its own shareable preview link. |  | Native, web | 2 Viewer (web) | Profile-Public, WebShowPage, Thread
66 | Viewer | Content & Sharing | As a viewer, I want to see an artist's profile including bio, discography, socials, ranking, show calendar, fan count, and streaming links. | See profile | Must | Pilot | Profile displays all listed fields; missing fields show a sensible empty state, not an error. |  | Native, web | 2 Viewer (web) | Profile-Public, WebShowPage, Thread
67 | Viewer | Content & Sharing | As a viewer, I want to message an artist from their profile. | Send Message | Should | Phase 2 | Message opens a DM thread with that artist. |  | Native, web | 2 Viewer (web) | Profile-Public, WebShowPage, Thread
68 | Viewer | Content & Sharing | As a viewer, I want to share an artist's profile to other platforms. | Share profile | Should | Phase 2 | Share generates a shareable profile link with preview. |  | Native, web | 2 Viewer (web) | Profile-Public, WebShowPage, Thread
69 | Viewer | Trust & Safety | As a viewer, I want to report a user or piece of content. | Censor Content | Should | Phase 2 | Report submits a ticket with reason to the admin queue. | Gap | Native, web | 6 Hardening | Show, YT-Show, PrivacySettings, BlockedWords
70 | Viewer | Trust & Safety | As a viewer, I want to block a specific user. | Blocklist User | Should | Phase 2 | Blocked user's comments/messages to this viewer are hidden. | Gap | Native, web | 6 Hardening | Show, YT-Show, PrivacySettings, BlockedWords
71 | Admin | User Management | As admin, I want to see all users on the platform. | See profile | Must | Phase 2 | Admin console lists all users with search/filter by role. |  | Web (admin console) | 6 Hardening (admin console, not yet designed) | Not designed
72 | Admin | User Management | As admin, I want to help users reset their password. | Log in | Should | Phase 2 | Admin can trigger a password reset flow for a specified user. |  | Web (admin console) | 6 Hardening (admin console, not yet designed) | Not designed
73 | Admin | User Management | As admin, I want to enable and disable users. | Enable user | Should | Phase 2 | Toggling status immediately restricts/restores that user's login ability. |  | Web (admin console) | 6 Hardening (admin console, not yet designed) | Not designed
74 | Admin | User Management | As admin, I want to blocklist users. | Blocklist User | Should | Phase 2 | Blocklisted user cannot log in or interact with the platform. |  | Web (admin console) | 6 Hardening (admin console, not yet designed) | Not designed
75 | Admin | User Management | As admin, I want to delete a user account. | Delete user | Should | Phase 2 | Deletion requires confirmation and follows the stated data retention policy. |  | Web (admin console) | 6 Hardening (admin console, not yet designed) | Not designed
76 | Admin | User Management | As admin, I want caution prompts for every edit or enable/disable decision, so that irreversible mistakes are avoided. | Enable user / Blocklist User | Should | Phase 2 | A confirmation dialog appears before any destructive or access-changing action completes. |  | Web (admin console) | 6 Hardening (admin console, not yet designed) | Not designed
77 | Admin | Content Moderation | As admin, I want to access and monitor every piece of content on the platform. | Censor Content | Must | Pilot | Admin console surfaces live and recorded content across all artists. |  | Web (admin console) | 6 Hardening (admin console, not yet designed) | Not designed
78 | Admin | Content Moderation | As admin, I want to censor content based on platform standards. | Censor Content | Must | Pilot | Admin can hide/remove flagged content; action is logged. |  | Web (admin console) | 6 Hardening (admin console, not yet designed) | Not designed
79 | Admin | Content Moderation | As admin, I want to force-stop content viewing on the platform. | Censor Content | Should | Phase 2 | Admin can end a live session immediately; all viewers are disconnected with a clear message. |  | Web (admin console) | 6 Hardening (admin console, not yet designed) | Not designed
80 | Admin | Content Moderation | As admin, I want to review and respond to user-submitted reports of content or users. | Censor Content | Should | Phase 2 | Reported items appear in a queue with the reporter's reason and a resolution action. | Gap | Web (admin console) | 6 Hardening (admin console, not yet designed) | Not designed
81 | Admin | Platform Monitoring | As admin, I want to see live shows for all artists, with a thumbnail and artist name. | See Live Competitions | Should | Phase 2 | Admin dashboard lists all current live shows with thumbnail and name. |  | Web (admin console) | 6 Hardening (admin console, not yet designed) | Not designed
82 | Admin | Platform Monitoring | As admin, I want to see and watch recorded shows for all artists. | Watch recorded show | Should | Phase 2 | Admin can browse and play back any artist's recorded content. |  | Web (admin console) | 6 Hardening (admin console, not yet designed) | Not designed
83 | Admin | Platform Monitoring | As admin, I want to monitor the onboarding flow for artists and viewers. | See profile | Could | Phase 3 | Admin sees completion rate/drop-off points in the sign-up flow. |  | Web (admin console) | 6 Hardening (admin console, not yet designed) | Not designed
84 | Admin | Platform Monitoring | As admin, I want to see and analyze artist analytics and data. | See artists Chart | Should | Phase 2 | Admin can view aggregate and per-artist analytics. |  | Web (admin console) | 6 Hardening (admin console, not yet designed) | Not designed
85 | Admin | Competitions | As admin, I want to create and manage genre-based competitions, so that artist competitions run smoothly. | Enter competitions | Should | Phase 2 | Admin can create a competition, set genre/dates, and view entries. | Gap | Web (admin console) | 6 Hardening (admin console, not yet designed) | Not designed
86 | Admin | Competitions | As admin, I want to resolve competition judging disputes. | Enter competitions | Could | Phase 3 | Disputed entries are flagged with a resolution workflow and outcome recorded. | Gap | Web (admin console) | 6 Hardening (admin console, not yet designed) | Not designed
87 | Admin | Financial Oversight | As admin, I want to see each artist's earnings. | See Artist Financials | Should | Phase 2 | Admin console shows per-artist earnings breakdown. |  | Web (admin console) | 6 Hardening (admin console, not yet designed) | Not designed
88 | Admin | Financial Oversight | As admin, I want to see the platform's total earnings. | See Platform Financials | Should | Phase 2 | Admin dashboard shows aggregate platform revenue over a selectable period. |  | Web (admin console) | 6 Hardening (admin console, not yet designed) | Not designed
89 | Admin | Financial Oversight | As admin, I want to handle payment disputes and refund requests. | See Platform Financials | Should | Phase 2 | Disputed transactions appear in a queue with refund/deny actions. | Gap | Web (admin console) | 6 Hardening (admin console, not yet designed) | Not designed
90 | Guest | Sign-up & Onboarding | As a guest, I want to watch for up to 60 seconds before I am asked to sign up, so that I see the product working before I meet a form. | Guest preview | Must | Phase 2 | Timer counts total watching on the device across every video, so swiping does not reset it. A chip appears at about 50 seconds. At 60 seconds, or on the first react, comment, vote, follow, remind me, message or support tap, a one-page sign-up opens and the tapped action completes after sign-up. The timer is stored on the device: a nudge, not a security control. | Added 1 Oct | Native, web | 2 Viewer (web) | Main, Discover-Preview, SignUp, YT-GuestSignUp | Decided 29 Sept. In the YouTube flow the player shrinks to 200 x 356 beside the sheet instead of being dimmed behind it.
91 | Guest | Sign-up & Onboarding | As a new user, I want a one-page sign-up I can finish in under a minute, so that I start watching and chatting quickly. | One-page sign-up | Must | Phase 2 | Apple, Google or email; watch or perform; name; username or stage name; date of birth; location pre-filled from the device; Terms, Community Guidelines and privacy accepted in one line. Genre and photo move to onboarding. Sign in with Apple is offered wherever Google login is. | Added 1 Oct | Native, web | 2 Viewer (web) | SignUp, Login | Replaces the long sign-up in rows 1 and 42. Legal name is verified at first cash-out only. No subscription at sign-up.
92 | Guest | Sign-up & Onboarding | As the platform, I want an 18+ gate at sign-up, so that only adults use a live video product with chat and messages. | Age gate | Must | Phase 2 | Date of birth is the gate. Under-18s see a kind stop screen and the date of birth is not stored. The sign-up flow lets a stronger age assurance step be inserted later without a redesign. | Added 1 Oct | Native, web | 2 Viewer (web) | UnderAge, SignUp | Online Safety Act position at launch: self-declared date of birth.
93 | Viewer | Sign-up & Onboarding | As a viewer, I want a short, skippable first run, so that Discover knows my taste without blocking me from watching. | Viewer onboarding | Should | Phase 2 | Pick three or more genres; follow suggested artists including new ones; notification permission asked after the first follow or first remind me, never on first launch. Skippable, resumable, never blocks watching. | Added 1 Oct | Native, web | 2 Viewer (web) | ViewerOnboarding, NotificationPrompt
94 | Viewer | Discover | As a viewer, I want a full-screen vertical feed with live shows first, so that I am watching music within seconds. | Discover feed | Must | Phase 2 | Cards snap one per swipe in this order: live from artists I follow, live matching my genres, starting soon (countdown with Remind me), clips and recordings. A fixed share goes to new artists. When nothing is live it opens on Starting soon, then clips. Never empty. A view counts after 30 seconds. Only one live player is active at a time; neighbours show a still image. | Added 1 Oct | Native, web | 2 Viewer (web) | Main, DiscoverEmpty, LiveLoading | Feed is a precomputed read model (see Scaling tab). Extends row 52.
95 | Viewer | Discover | As a viewer, I want simple gestures and sound defaults in the feed, so that browsing feels natural. | Feed gestures | Should | Phase 2 | Tap a live card opens the show; tap a clip pauses or plays; double tap likes; long press offers not interested, report, share; tap stage name opens the profile. Native sound is on and respects the silent switch; web shows a 'Tap for sound' chip. | Added 1 Oct | Native, web | 2 Viewer (web) | Main
96 | Viewer | Live tab | As a viewer, I want to see what is live now and what is coming, so that I can join or set a reminder. | Live tab | Must | Phase 2 | Live now grid (followed artists first); Starting soon with countdown; Upcoming by day with genre and Solo or Versus filters; Competitions (mock until built). Every upcoming show offers Remind me, Add to calendar and Share. | Added 1 Oct | Native, web | 2 Viewer (web) | Live, LiveLoading | Extends row 52.
97 | Viewer | Search | As a viewer, I want search that remembers and never dead-ends, so that I can find artists, shows and genres. | Search | Should | Phase 2 | Recent searches (remove one, clear all); suggestions artists first then shows then genres; results tabs Top, Artists, Live and upcoming, Recordings, Genres; no results suggests close spellings and the nearest genre. History can be paused or cleared; guests search without saved history. | Added 1 Oct | Native, web | 2 Viewer (web) | Search, SearchResults, SearchNoResults, PrivacySettings | Extends row 52.
98 | Viewer | Watching (YouTube) | As a viewer, I want to watch the show in an embedded YouTube player with nothing covering it, so that the picture is clean and the platform stays within YouTube's rules. | Watch in embedded player | Must | Phase 2 | Player is at least 200 x 200 and never overlaid or obscured, with no click-blocker. Chat, emoji, a reactions tab, votes, Support, Share and Report sit around it. Playback goes through a PlayerSource interface so Loudentify's own delivery can replace it by configuration. Only viewers use the YouTube flow; artists never do. | Added 1 Oct | Native, web, website | 2 Viewer (web) | YT-Show, YT-Waiting | Decision 1 Oct: YouTube first, own hosting later. Replaces the delivery assumption behind row 50.
99 | Viewer | Watching (YouTube) | As a viewer, I want the picture to grow and shrink as I use the screen, so that I get a big picture without losing chat and voting. | Resizing show layout | Must | Phase 2 | Phone default about 304 x 540 with 44px side buttons. Bigger gives about 340 x 604 and chat collapses to one line. A vote sheet shrinks the picture to 270 wide. Guest sign-up uses 200 x 356. Fold and tablet use the 768 layout with a 360 x 640 picture and chat beside it. Computer uses 405 x 720 between info and chat. The website show page uses the same frame. | Added 1 Oct | Native, web, website | 2 Viewer (web) | YT-Show, YT-Focus, YT-Prompt, YT-FoldShow, WebYT-Show, WebYT-ShowPage
100 | Viewer | Watching (YouTube) | As a viewer, I want to watch a Versus show in three views, so that I can follow the conversation and each performance. | Versus viewing | Must | Phase 2 | The picture is composed by the platform with no per-viewer change. Conversation: screen split half and half, top and bottom. Artist A performing: A fills the frame and B sits in a small portrait window in the lower right (about 31% of frame width). Artist B performing: the mirror. The window is neither too small to see nor big enough to crowd the performer. | Added 1 Oct | Native, web, website | 2 Viewer (web) | YT-VersusTalk, YT-Versus, YT-VersusB, YT-FoldVersus, WebYT-VersusTalk, WebYT-VersusA | Replaces the earlier single Versus layout (featured performer large, other as thumbnail).
101 | Viewer | Voting | As a viewer, I want to vote in artist prompts and Versus rounds, so that I help decide outcomes. | Vote | Must | Phase 2 | One vote each, changeable until voting closes. Voting is open in all three Versus views ('Who moved you this round?'). Votes and Support are stamped with the viewer's playback position, with a short grace window when voting closes, so they line up with what the viewer sees. Competition outcomes come from verified-fan votes, never token volume. | Added 1 Oct | Native, web | 2 Viewer (web) | YT-Prompt, YT-Versus | Extends row 61 and 62. Delay alignment is a test in Hardening.
102 | Viewer | Reactions | As a viewer, I want free reactions during a show, so that I can show feeling without typing. | Reactions | Should | Phase 3 | Reactions are stamped with playback position. The chat box keeps room for a reactions tab beside emoji. Versus reactions carry the artist they are for, so blended scoring is possible. Reaction design itself is on hold until after the UI pass. | Needs decision | Native, web | 2 Viewer (web) | Show, YT-Show | Design on hold. Versus reactions need a schema change before they can count for A or B.
103 | Viewer | Waiting room | As a viewer, I want a waiting room before a show starts, so that I know when it begins and can set a reminder. | Waiting room | Should | Phase 2 | 15-minute countdown, pre-show loop, artist card, Remind me for late arrivals, chat open early. | Added 1 Oct | Native, web | 2 Viewer (web) | WaitingRoom, YT-Waiting
104 | Viewer | Show end | As a viewer, I want a useful end of show, so that I can follow, watch back or find the next show. | End card | Should | Phase 2 | Shows the Versus result (today it is voice only), Follow, watch the recording later, the artist's next show and the next live show. | Added 1 Oct | Native, web | 2 Viewer (web) | EndCard
105 | Viewer | Watching (YouTube) | As a viewer on a phone, I want picture-in-picture when I leave the app mid-show, so that I can keep watching. | Picture-in-picture | Could | Phase 3 | Native leaving the app mid-show continues playback in picture-in-picture where the embedded player allows it. | Needs decision | Native | 4 Native apps | Show | Embedded YouTube may limit picture-in-picture. Decide after testing on real devices.
106 | Viewer | Privacy | As a viewer, I want to be asked before embedded-player cookies are set, so that my privacy choices are respected. | Cookie consent | Must | Phase 2 | Cookie banner appears before analytics, marketing or (where required) YouTube embed cookies run. Privacy-enhanced embed domain used. Privacy notice says the picture is carried by YouTube and that Loudentify does not receive viewer identity from YouTube. | Added 1 Oct | Web, website, native | 5 Website | WebLegal | UK PECR. Needs legal wording.
107 | Viewer | Financial Support | As a viewer, I want to spend tokens I already hold to support an artist, so that I can show appreciation in the moment. | Support with tokens | Must | Phase 2 | Support sheet: pick an amount, confirm. Thank-you moment with no jackpot or slot-machine visuals. Every write is idempotent by client id, so a double tap pays once. Daily and monthly spending limits apply; the fan can set a lower limit of their own. | Added 1 Oct | Native, web | 2 Viewer (web) | SupportSheet, Wallet | Extends rows 61 and 62.
108 | Viewer | Financial Support | As a viewer, I want to buy tokens on the web and see my balance in the app, so that payments stay out of the native app. | Wallet and token purchase | Must | Phase 2 | Tokens are bought on loudentify.app/wallet through the payment provider; the balance then updates in the app. The native apps have no buy button and no payment link. Before release, check whether store rules allow the app to mention the website for top-ups. | Added 1 Oct | Native (balance), web (buy) | 2 Viewer (web) | Wallet, WebBuyTokens | Payment provider not yet chosen.
109 | Viewer | Engagement | As a viewer, I want to message artists, subject to their messaging setting, so that I can reach them from their profile. | Messaging | Should | Phase 2 | Viewers and artists can both message at launch. 'Who can message me' offers everyone, people I follow, or nobody. Blocked accounts and a hidden-words filter are available. | Added 1 Oct | Native, web | 2 Viewer (web) | Inbox, Thread, PrivacySettings, BlockedWords | Extends row 67.
110 | Viewer | Auth & Profile | As a viewer, I want to become an artist from my profile, so that I can perform when I am ready. | Become an artist | Should | Phase 2 | Viewers see three tabs, with no Create button. A Become an artist card sits on their profile and adds a stage name and unlocks the artist console. | Added 1 Oct | Native, web | 2 Viewer (web) | ViewerProfile, BecomeArtist | Decided 30 Sept: Create button hidden for viewers.
111 | Artist | Auth & Profile | As an artist, I want to connect my YouTube account when I sign up, so that my show can go out on my own channel. | Connect YouTube | Must | Phase 2 | Artist connects a Google/YouTube account (YouTube only) with the narrowest scope that lets Loudentify create and end broadcasts. Readiness is checked at onboarding: the channel must be allowed to live stream (a new channel can take about a day to enable). The artist can disconnect at any time, effective immediately. Tokens are encrypted, never returned to a client, and every connect and disconnect is audited. | Added 1 Oct | Native, web | 3 Artist and live pipeline | ArtistOnboarding, AccountSettings | Requires Google verification for the live streaming scope (see row 'Google verification').
112 | Artist | Auth & Profile | As an artist, I want a plain artist agreement, so that I understand my rights, my duties and what YouTube's rules mean for me. | Artist agreement | Must | Phase 2 | Covers rights, conduct, YouTube terms (strikes, music rights, originals only), content responsibility, and disconnect and deletion. The training-data choice is a separate line, never inside the terms sentence. | Added 1 Oct | Native, web | 3 Artist and live pipeline | ArtistAgreement | Needs a solicitor's review before launch.
113 | Artist | Auth & Profile | As an artist, I want to switch off the use of my performance for the AI director, so that I stay in control of my footage. | Training-data choice | Must | Phase 2 | A separate line at sign-up for performers only, on by default (legitimate interests basis), switchable in Settings at any time with effect from that moment and audited. Used only for the artist's own performance, only for the director model, only inside Loudentify. Viewers are excluded. In Versus the exclusion applies per artist on the source camera tracks; a composite is used only if both artists have it on. | Added 1 Oct | Native, web | 1 Foundations | ArtistAgreement, AccountSettings | Architecture v2. Needs a written Legitimate Interests Assessment and legal review.
114 | Artist | Auth & Profile | As an artist, I want to set up my stage once, so that each show starts from saved settings. | Set up my stage | Should | Phase 2 | Photo, bio, genres; pick a mic; pair a first camera; save it as a place (for example 'Living room'); Book your first show nudge; progress card on the profile until done. Skippable and resumable. | Added 1 Oct | Native, web | 3 Artist and live pipeline | ArtistOnboarding
115 | Artist | Scheduling | As an artist, I want to schedule a show at least 30 minutes ahead, so that fans can plan and my kit is ready. | Schedule a show | Must | Phase 2 | Solo or Versus; date, start time and length (10 minutes to over an hour); title, genre, cover; pick the place; optionally attach backing tracks, cue sheet and B-roll. Earliest start offered is 30 minutes from now. No unscheduled go-live. | Added 1 Oct | Native, web | 3 Artist and live pipeline | Create, Schedule | Supersedes row 10 where it allows going live at any time.
116 | Artist | Scheduling | As an artist, I want to invite another artist to a Versus show, so that we can perform together. | Versus invite | Must | Phase 2 | Invite link sent from the schedule screen; the show confirms when the other artist accepts. | Added 1 Oct | Native, web | 3 Artist and live pipeline | Schedule, VersusInvite | Extends row 30.
117 | Artist | Scheduling | As an artist, I want reminders and a share card for my show, so that I and my fans turn up. | Show reminders | Should | Phase 2 | Artist reminders at 24 hours, 4 hours, 1 hour and 30 minutes; only reminders still in the future fire. A Share your show card carries the public show link. Viewers get Remind me. | Added 1 Oct | Native, web | 3 Artist and live pipeline | NotificationSettings, WebShowPage
118 | Artist | Kit Check | As an artist, I want a pre-show check that tells me what to fix, so that nothing fails in front of an audience. | Kit Check | Must | Phase 2 | Checklist of outcomes, each green, amber or red with one fix: mic sending real signal (raw input); each camera holds frames for two minutes; connection strong enough; devices charging with Do Not Disturb on; headphones wired or Bluetooth latency checked; nothing streams during the check. | Added 1 Oct | Native, web | 3 Artist and live pipeline | KitCheck, WebKitCheck | Lessons from 20 Sept: mic died, a camera passed a connect check then stalled 283 times.
119 | Artist | Kit Check | As an artist, I want to frame myself inside the exact windows viewers will see, so that I look right in every view. | Frame check | Must | Phase 2 | Shows only my own camera, never the YouTube picture, cropped to the three broadcast windows (conversation half, full performing frame, corner window) with framing guides. | Added 1 Oct | Native | 3 Artist and live pipeline | YT-KitCheck
120 | Artist | Live Performance - Solo/Versus | As an artist, I want a countdown that takes me live on time, so that I do not have to press anything at the last second. | Countdown and go-live | Must | Phase 2 | A 60-second countdown at slot time. If the artist is in Kit Check they go live automatically. Viewers see the waiting room. | Added 1 Oct | Native, web | 3 Artist and live pipeline | Countdown
121 | Artist | Live Performance - Solo/Versus | As an artist, I want a minimal live console, so that I can perform without technical clutter. | Live console | Must | Phase 2 | Shows what viewers see now, a small self-view and the viewer count; comments collapsible; prompt and vote buttons; director shows Auto with manual cuts closed by default; Fix sheet one tap away; End show by press and hold. Solo shows keep this console under YouTube delivery. | Added 1 Oct | Native, web | 3 Artist and live pipeline | Console, TabletConsole
122 | Artist | Live Performance - Solo/Versus | As a Versus artist, I want Conversation and Perform buttons, so that I control what viewers see. | Versus view control | Must | Phase 2 | The console shows exactly the composed frame that goes to YouTube; viewers see it a few seconds behind. Conversation and Perform change the view. The current view is a show-level fact and every change is audited. | Added 1 Oct | Native, web | 3 Artist and live pipeline | YT-ArtistTalk, YT-ArtistPerform, WebYT-Artist | Replaces the earlier 'slot A switches who is featured' behaviour.
123 | Artist | Live Performance - Solo/Versus | As a Versus artist, I want a stage handover to be confirmed, so that nobody takes the stage by accident. | Stage handover | Must | Phase 2 | Tapping Perform while the other artist is performing sends a stage request and shows 'Asking [Artist]'. The performing artist confirms with 'Hand over the stage' or declines with 'Not yet'. Switching to Conversation is immediate. All steps audited. | Added 1 Oct | Native, web | 3 Artist and live pipeline | YT-ArtistRequest, YT-ArtistHandover | Decided 1 Oct: confirmed first, not last-tap-wins.
124 | Artist | Live Performance - Solo/Versus | As an artist, I want one-tap recovery mid-show, so that a failure never means logging out. | Fix sheet | Must | Phase 2 | From one sheet: switch mic, recheck cameras, reconnect. Switching a mic rewires the live mix in place. If a camera stalls twice in a minute, the sheet shows it before a viewer notices. | Added 1 Oct | Native, web | 3 Artist and live pipeline | FixSheet | Agreed fix from 20 Sept.
125 | Artist | Live Performance - Solo/Versus | As an artist, I want a warning before I leave the app, so that I do not lose the camera by accident. | Foreground rule | Must | Phase 2 | Performer and camera devices stay in the foreground for the whole show; the app warns before the artist switches away (iOS stops camera capture in the background). | Added 1 Oct | Native | 3 Artist and live pipeline | Console, CameraMode
126 | Artist | Multi-Camera & Production | As an artist, I want to pair a phone as a camera with one QR code, so that adding a camera is easy. | Pair a camera | Must | Phase 2 | QR from Settings, Devices or Kit Check. The camera phone needs no account and gets a device credential scoped to one artist, one slot and one show window, publish only. It shows viewfinder, role, connection and ON AIR. It reconnects to the same slot next time. One feed per physical device, using that device's own camera. | Added 1 Oct | Native, web | 3 Artist and live pipeline | CameraMode, DevicesSettings | Extends row 12.
127 | Artist | Multi-Camera & Production | As an artist, I want to set up each camera once, so that the picture is right from the first frame. | Camera settings | Should | Phase 2 | Exposure and focus lock; white balance; device zoom (the phone's own camera zoom, including lens switching on multi-camera phones; default 1.2x, editable per camera); digital zoom only as a fallback capped at 1.2x when device zoom is unavailable on that phone or lens; moving zoom and pan with durations (2s, 4s, 8s, custom; pan off by default); portrait by default. Aperture is removed. LUTs and background blur are not at launch. | Added 1 Oct | Native | 3 Artist and live pipeline | CameraSettings | Supersedes rows 15 and 16 on digital zoom. 12 Oct 2026: digital fallback capped at 1.2x when device zoom is unavailable (docs/DECISIONS.md 2026-10-12, supersedes "never a digital crop").
128 | Artist | Multi-Camera & Production | As an artist, I want to choose which moves the director may use, so that the show suits my style. | Director moves | Must | Phase 2 | Auto director is on by default. The artist switches each move on or off (cuts, close-ups, wide shots, moving zoom, pan, B-roll inserts) and the director uses only what is on. Manual cuts panel is closed by default. The shot grammar is not changed. | Added 1 Oct | Native, web | 3 Artist and live pipeline | DirectionSettings | Supersedes row 19 (default off).
129 | Artist | Multi-Camera & Production | As an artist, I want to choose and protect my sound, so that my voice is right every show. | Audio settings | Must | Phase 2 | Microphone picker; mic health watched on the raw input with in-place repair; vocal preset saved per place; backing track balance; headphone latency check. Echo and noise processing stay off and are not shown. | Added 1 Oct | Native, web | 3 Artist and live pipeline | AudioSettings
130 | Artist | Multi-Camera & Production | As an artist, I want a library of my tracks, cues and B-roll, so that I can attach them when I schedule. | Studio library | Should | Phase 2 | Backing tracks, cue sheets and B-roll (500 MB total, 100 MB per file, muted on upload). Places are saved bundles of mic, preset and cameras. | Added 1 Oct | Native, web | 3 Artist and live pipeline | StudioLibrary
131 | Artist | Multi-Camera & Production | As an artist, I want a second person to run controls for me, so that I can focus on performing. | Operator | Could | Phase 3 | Operator invite link; web console with all feeds, manual cuts, prompts and votes; Go live and End show only if the artist grants them. The grant expires with the show and can be revoked mid-show. | Deferred | Web | 3 Artist and live pipeline | WebOperator, OperatorInvite | UI designed now, backend later.
132 | Artist | Content & Sharing | As an artist, I want a post-show summary and a say over the recording, so that I know how it went and who can watch it. | Post-show | Should | Phase 2 | Summary with peak viewers, watch time, votes and tokens received. Recording-ready notification and visibility Public, Unlisted or Private. A Make a clip prompt. | Added 1 Oct | Native, web | 3 Artist and live pipeline | PostShow
133 | Artist | Content & Sharing | As an artist, I want to make short clips, so that I can bring new people to the full show. | Make a clip | Should | Phase 2 | Trim up to 90 seconds; frame for 9:16 with a caption safe area; add a title; Loudentify mark and my handle go on the export; share through the system share sheet or save to the phone. | Added 1 Oct | Native, web | 3 Artist and live pipeline | ClipEditor | Extends row 32.
134 | Artist | Analytics & Ranking | As an artist, I want per-show insights, so that I learn what worked. | Insights | Should | Phase 2 | Peak viewers, watch time, votes and followers gained, per show. | Added 1 Oct | Native, web | 3 Artist and live pipeline | Insights | Extends row 36.
135 | Artist | Auth & Profile | As an artist, I want one profile that shows my console to me and the public page to everyone else, so that nothing private leaks. | Profile owner mode | Must | Phase 2 | The server decides the mode. A non-owner never receives owner data. Owner mode shows a status strip ('Next show Sat 19:30 Stage ready' or '1 thing to fix'), Schedule, Kit check, New clip, a shows tab with visibility toggles, clips and insights. Menu sits top right. | Added 1 Oct | Native, web | 3 Artist and live pipeline | Profile-Owner, Profile-Public, ProfileEmpty | Extends rows 3 and 4. Permission test is mandatory.
136 | Artist | Financial | As an artist, I want to see my viewer-hours and prepaid packs, so that I know my allowance. | Allowance | Must | Phase 2 | Shows hours used and borrowed, show slots left and prepaid packs (buying on web). A pack is offered when hours run low, never at sign-up. A show never cuts off when hours run out; it borrows and the offer comes after. | Needs decision | Native, web | 3 Artist and live pipeline | Allowance | What viewer-hours mean under YouTube delivery is undecided: they no longer track a media cost Loudentify pays.
137 | Artist | Financial | As an artist, I want my earnings shown in pounds, so that I know what I will be paid. | Earnings | Must | Phase 2 | Tokens received shown in pounds at the artist share of 72.5%, recorded at the moment of the transaction. Pending and available balances, payout history. Competition prize money appears labelled as a prize. | Added 1 Oct | Native, web | 3 Artist and live pipeline | WalletPayouts, WebEarnings | Extends rows 33 to 35.
138 | Artist | Financial | As an artist, I want a safe, verified cash-out, so that payouts reach me and fraud is blocked. | Cash out | Must | Phase 2 | First cash-out needs an identity check by the provider (legal name, date of birth, address, ID). Loudentify keeps only a pass or fail and a reference. Payout account is held by the provider. Re-authentication is required for payout and email changes. No manual override without two approvers. | Added 1 Oct | Web, native (status) | 3 Artist and live pipeline | WebIdentity, WalletPayouts | Identity and payment providers are not chosen yet.
139 | Platform | Live pipeline | As the platform, I want to build one composed portrait picture, so that artists, recordings and viewers all see the same show. | Composed picture | Must | Phase 2 | Solo is the director's output. Versus has the three views. Same picture goes to the artists' screens, the recording and (through YouTube) the viewers. Loudentify logo is burned in before it leaves. Corner window sits lower right at about 31% of frame width. | Added 1 Oct | API | 3 Artist and live pipeline |  | Compositor must have its own tests (three views, window position, handover).
140 | Platform | Live pipeline | As the platform, I want one egress to stream to YouTube and record at once, so that a recording cannot go missing. | Egress to YouTube | Must | Phase 2 | One egress sends the composed picture over RTMP to YouTube (to both artists' channels in Versus) and writes the recording and training copy. Stream keys are per show, never logged, never sent to a client, and rotated after the show. | Added 1 Oct | API | 3 Artist and live pipeline |  | Only one egress per show keeps cost down.
141 | Platform | Live pipeline | As the platform, I want to create and end the YouTube broadcast with the show, so that artists never touch YouTube Studio. | Broadcast lifecycle | Must | Phase 2 | Broadcast created when the show is scheduled, live at the slot, ended with the show. YouTube's own live chat and comments are switched off where the API allows. In Versus, viewer counts are aggregated across both channels. | Added 1 Oct | API | 3 Artist and live pipeline
142 | Platform | Live pipeline | As the platform, I want delivery problems to never lose a show, so that artists keep their audience. | Delivery failure handling | Must | Phase 2 | If YouTube delivery drops, artists keep performing, recording continues, viewers see an honest reconnecting state, and the egress retries the same broadcast then creates a new one. Every step is audited. | Added 1 Oct | API | 3 Artist and live pipeline | ShowOffline | Add to failure drills.
143 | Platform | Delivery | As the platform, I want to swap delivery without rewriting screens, so that we can move to our own hosting when funded. | PlayerSource interface | Must | Phase 2 | A PlayerSource interface with two implementations, youtube (first) and loudentify-llhls (later), chosen by configuration per show or region. Clients never depend on which one is used. | Added 1 Oct | API, all clients | 2 Viewer (web) |  | Decision 1 Oct: YouTube first, own hosting later.
144 | Platform | Metering | As the platform, I want to count a view after 30 seconds, so that artists are not charged for scrolling past. | Viewer-hour metering | Must | Phase 2 | Count comes from the embedded player's playback events, reported by the viewer's client with the pseudonymous viewer id. Rate-limited, de-duplicated per viewer and show, sanity-checked against YouTube's concurrent viewers. Separate event stream from the ledger, reconciled to it, never blocks playback, and can be rebuilt afterwards. | Needs decision | API | 3 Artist and live pipeline |  | Build either way; the allowance rules depend on the viewer-hours decision.
145 | Platform | Reliability | As the platform, I want a fixed order of what to drop when something fails, so that the performance is always protected. | Degrade, never stop | Must | Phase 2 | Order: analytics, viewer counts, comments to read-only, single camera (in Versus the healthy artist fills the frame), video quality, then end with an honest message and keep the recording. If only YouTube delivery fails the show is not ended. Money and safety controls fail closed. | Added 1 Oct | API | 6 Hardening | ShowOffline
146 | Platform | Cost | As the business, I want to track cost per show-hour and YouTube quota, so that pricing rests on facts. | Cost tracking | Should | Phase 2 | Cost per show-hour (egress, compute, storage) tracked from the first show; concurrent shows capped per region at launch; alert when YouTube API quota is near its limit. | Added 1 Oct | API | 3 Artist and live pipeline |  | Replaces cost per viewer-hour as the key metric.
147 | Platform | Access control | As the platform, I want a permission model built on organisations, so that access is right now and scales to labels later. | Permission model | Must | Phase 2 | Roles are granted per organisation; a solo artist is an organisation of one. Row-level security in the database; permission checked at the data layer, never the screen. Permission tests for every endpoint and role, including negative cases. | Added 1 Oct | API | 1 Foundations |  | Highest-value control in the architecture.
148 | Platform | Access control | As the platform, I want short-lived sessions with safe refresh, so that a stolen token is caught quickly. | Tokens and sign-in | Must | Phase 2 | Access tokens last 15 minutes; refresh tokens are bound to a device, rotate on use, and reuse of an old one revokes the whole family. Passkeys from launch with Apple and Google sign-in. Step-up authentication on payout, email and identity changes. | Added 1 Oct | API | 1 Foundations |  | Extends rows 2, 43 and 46.
149 | Platform | Audit | As the platform, I want a separate tamper-evident audit log, so that we can prove who did what. | Audit log | Must | Phase 2 | Own store, credentials and account. No update or delete from any application role. Each entry carries a hash of the previous one and a daily root hash is published internally. Queryable by actor, subject, action, time and correlation id. Records that an action happened, not private message or card contents. Security and financial entries kept six years. | Added 1 Oct | API | 1 Foundations |  | Build first: SOC 2 needs a year of continuous evidence.
150 | Platform | Audit | As the platform, I want the right events logged, so that the log answers real questions. | Audit events | Must | Phase 2 | Logs authentication, access to another person's data (with ticket reference), money, consent and privacy, content decisions, grants, configuration, third-party connections, show control (view changes, stage requests, legal holds) and release and agent actions. | Added 1 Oct | API | 1 Foundations
151 | Platform | Money | As the platform, I want a double-entry append-only ledger, so that every balance can be explained. | Ledger | Must | Phase 2 | Every movement is two matching entries; balances are derived; corrections are reversing entries; every write is idempotent by client id; reconciled daily against the payment provider; artist share (72.5%) recorded at the transaction. | Added 1 Oct | API | 1 Foundations |  | Ledger property tests are required.
152 | Platform | Privacy | As the platform, I want consent and preferences recorded and audited, so that we can prove what each person agreed to. | Consent records | Must | Phase 2 | Records terms acceptance, training-data choice and marketing consent, each change audited. Withdrawing is as easy as giving and takes effect immediately. | Added 1 Oct | API | 1 Foundations | AccountSettings, ArtistAgreement
153 | Platform | Privacy | As a user, I want my data downloaded and my account closed properly, so that my rights are met automatically. | Data rights | Must | Phase 2 | Data is classified in the schema. Download my data (profile, shows, wallet history, comments, notifications) within the statutory window. Close my account hides the profile and makes recordings private, then hard-deletes personal data after a grace period, keeping only what the ledger requires. The screen says what is kept and why, disconnects YouTube and deletes the tokens, and says that content already on the artist's YouTube channel must be removed there. | Added 1 Oct | Native, web | 6 Hardening | AccountSettings | Extends rows 7, 8, 48 and 49.
154 | Platform | Privacy | As the platform, I want personal data kept in the UK or EU, so that we meet residency expectations. | Data residency | Must | Phase 2 | Personal data and private recordings stay in a UK or EU region. The live picture on YouTube is public and outside our region control, and the privacy notice and artist agreement say so. | Added 1 Oct | API | 1 Foundations
155 | Platform | Privacy | As an artist, I want my recordings kept safely and only frozen when needed, so that my catalogue is protected. | Retention and legal hold | Must | Phase 2 | Recordings kept until the artist deletes them; hot for 30 days then cold; clips stay hot. A legal hold freezes a reported or disputed show's recording until lifted (scoped, time-limited, reviewed, audited). Artists are told well before any time limit. | Added 1 Oct | API | 3 Artist and live pipeline |  | Our egress recording is the evidence copy.
156 | Platform | Compliance | As the business, I want the privacy assessments written before launch, so that we are ready for scrutiny. | DPIA and LIA | Must | Phase 2 | Data Protection Impact Assessment (live video of identifiable people, payments, AI processing, YouTube as a recipient, the embed, the channel connection) and a Legitimate Interests Assessment, with legal review of the training-data basis and the biometric question. | Added 1 Oct | Documents | 6 Hardening |  | Drafts by Claude Code, review by a solicitor.
157 | Platform | Trust & Safety | As a viewer or artist, I want a one-tap report that reaches a real queue, so that harm is dealt with fast. | Report queue | Must | Phase 2 | Report on the show screen sends the show, timestamp and reporter to a moderation queue. Complaints and appeal route exist. Decisions are logged. | Added 1 Oct | Native, web | 6 Hardening | Show, YT-Show | Extends rows 40, 69 and 80.
158 | Platform | Trust & Safety | As an admin, I want to stop a show at once, so that harm on a live show ends immediately. | Stop show | Must | Phase 2 | Stopping removes the embed from Loudentify, ends the YouTube broadcast or makes it private where the API allows, and freezes our evidence recording. Audited. | Added 1 Oct | Web | 6 Hardening |  | Extends row 79.
159 | Platform | Trust & Safety | As the business, I want Online Safety Act duties met, so that we can lawfully run live video with chat. | OSA compliance | Must | Phase 2 | Written, current illegal-content risk assessment; terms with an appeal route; a named accountable founder; a documented escalation route for child sexual abuse material and threats to life; chat filters and hidden words on by default; new-artist show rate the team can actually watch. | Added 1 Oct | Documents, all | 6 Hardening | BlockedWords | Needs legal review.
160 | Platform | Trust & Safety | As the platform, I want abuse limits, so that bulk accounts and spam cannot damage votes or users. | Abuse limits | Should | Phase 2 | Rate limits on sign-up, comments, follows and token spending; device and network signals to catch bulk accounts; a quick route for an artist to report someone targeting them across shows. | Added 1 Oct | API | 6 Hardening |  | Competition vote integrity depends on real accounts.
161 | Platform | Financial Oversight | As the business, I want financial crime controls from day one, so that the platform is not used to launder money. | AML controls | Must | Phase 2 | Spending limits per day and month; alerts for a new account spending heavily, circular flows between a pair, many small accounts funding one artist, and a spike before a payout; separation of duties (the reviewer is not the approver and neither changes limits); suspicious activity reporting with a named person and documented route; no payout before an identity check. | Added 1 Oct | API, web | 6 Hardening |  | Extends rows 87 to 89.
162 | Platform | Release | As the owner, I want separate staging and production with a gated promote, so that I test first and release deliberately. | Environments and promote | Must | Phase 2 | Local, staging and production use separate Supabase projects, keys and data. Pull requests merge into staging on green tests and the pipeline applies migrations. Production changes only through the promote workflow with a human approval, applying the same migration files with rollback scripts. Production credentials exist only as secrets of the production environment. | Added 1 Oct | Pipeline | 1 Foundations |  | Decided 1 Oct.
163 | Platform | Release | As the owner, I want a human to approve risky changes before production, so that an unattended build cannot ship a security flaw. | Protected paths | Must | Phase 2 | Changes to money, identity, permissions, row-level security and the audit log need a recorded human approval (Ugo or Korey) before promotion, and the promote workflow refuses without it. The build agent never holds production credentials. | Added 1 Oct | Pipeline | 1 Foundations
164 | Platform | Release | As the business, I want secrets protected and code scanned, so that a leaked key never reaches production. | Secrets and scanning | Must | Phase 2 | Secrets live in a manager, never in the repository or a chat. Secret scanning with push protection; dependency and container scanning in the pipeline; staging uses synthetic data only. | Added 1 Oct | Pipeline | 1 Foundations
165 | Platform | Observability | As the team, I want every journey step and every live show instrumented, so that we can react during a show and improve the product. | Instrumentation | Must | Phase 2 | Correlation id on every request through logs, traces and audit. Journey events: sign-up started and completed with its trigger, feed card seen, show joined and left, reminder set, Kit Check per item, go live, end show, clip shared, Versus view changes, stage request outcomes, Bigger used, leaving for YouTube. Per show: camera frames and stalls, raw audio level, egress frames and reconnects, YouTube state, delay. Tied to a pseudonymous viewer id. Alerts only for a failed show start, reconciliation mismatch, authentication spike, audit write failure, error budget burn, egress failure and quota near limit. | Added 1 Oct | API | 1 Foundations |  | Extends the Observability row on the Scaling tab.
166 | Platform | Performance | As a viewer, I want the app fast on a mid-range phone, so that I do not swipe away. | Performance budgets | Should | Phase 2 | App open to first video frame under 2 seconds; tap a live card to joining the show under 3 seconds including the YouTube player; no dropped frames scrolling; comment appears under 1 second; settings screens under 1 second; cursor pagination, never offsets; measured on real devices. | Added 1 Oct | Native, web | 6 Hardening
167 | Platform | Reliability | As the business, I want backups proven by a restore, so that recovery is a fact not a guess. | Backups and recovery | Must | Phase 2 | Point-in-time recovery with a 5-minute recovery point objective and a 1-hour recovery time objective; encrypted backups in a separate account; restore tested at least quarterly. Staging and production rebuild from the repository. | Added 1 Oct | Pipeline | 6 Hardening
168 | Platform | Compliance | As the business, I want an external penetration test and an incident plan, so that we are ready for real attacks. | Pen test and incident plan | Must | Phase 2 | Penetration test focused on access control between users and on money paths. Written incident plan naming who decides, who communicates and the 72-hour breach notification route. | Added 1 Oct | Documents | 6 Hardening
169 | Platform | Compliance | As the business, I want Google verification and an API quota plan in hand before the first public show, so that YouTube streaming is allowed at scale. | Google verification and quota | Must | Phase 2 | Google OAuth verification for the live streaming scope completed; default API quota understood and a request or plan in place before launch. | Needs decision | Documents | 3 Artist and live pipeline |  | Start early: Google's review can take weeks.
170 | Support | User Management | As a support agent, I want time-boxed access to one user's account state after a ticket opens, so that I can help without seeing private content. | Support access | Should | Phase 3 | Access only after a ticket is open, time-boxed, to the named user's account state. Never message contents or payout changes. Every view is audited. | Added 1 Oct | Web | 6 Hardening
171 | Finance | Financial Oversight | As finance, I want to review ledger and payouts separately from approving them, so that no one person can move money alone. | Payout review | Must | Phase 2 | Finance reviews ledger and payouts; approval is a different person; neither can change limits. Overrides need two approvers. | Added 1 Oct | Web | 6 Hardening
172 | Admin | Platform Monitoring | As the owner, I want engineers to have no standing production access, so that a stolen laptop cannot reach live data. | Break-glass access | Should | Phase 3 | Production access is requested, time-boxed, approved, logged and expires. | Added 1 Oct | Pipeline | 6 Hardening
173 | Platform | Website | As an artist or fan, I want public show pages with good previews, so that shared links work everywhere. | Public show pages | Must | Phase 2 | Links /show/..., /@username, /clip/... and /invite/... open the app when installed and the web otherwise. Pages carry Open Graph previews. Home has a live strip of real shows with Watch in browser. | Added 1 Oct | Website | 5 Website | WebShowPage, WebLiveUpcoming, WebHome | Extends rows 32, 64 and 68.
174 | Platform | Website | As a visitor, I want a clear website, so that I understand Loudentify and can sign up. | Website pages | Should | Phase 2 | Home with animated hero (respects reduced motion, never delays loading; real artists only), Live and upcoming, For artists, For fans, Pricing, Get the app, About, Contact, Help, Legal and Cookies. | Added 1 Oct | Website | 5 Website | WebHome, WebForArtists, WebForFans, WebPricing, WebGetApp, WebAbout, WebHelp, WebContact, WebLegal
175 | Platform | Cross-device | As a user on any device, I want every screen to handle loading, empty, error and offline states, so that nothing ever looks broken. | Five states and accessibility | Must | Phase 2 | Loading, empty, error, offline and success designed and built for every screen. Fold and tablet use the 768 layout. Contrast, 44px touch targets, screen reader labels and reduced motion are met. | Added 1 Oct | All | 2 Viewer (web) | StatesPatterns, ResponsiveRules, DesignSystem
176 | Platform | Native apps | As a user, I want iOS and Android apps that match the web, so that I can watch and perform from my phone. | Native apps | Must | Phase 2 | Built from shared code with the same flows, plus camera mode. Test builds installable on a phone through cloud builds. No payments in the native apps. | Added 1 Oct | Native | 4 Native apps

## Change log (1 Oct)
Type | Where | What changed | Why
Fix | PRD tab, header | Story 1 had overwritten the header row. A proper header row was restored and story 1 moved to row 2. Filter now covers every row. | The sheet had no column titles.
Added | PRD tab, IDs 90 to 176 | 87 new stories covering guests and sign-up, Discover, YouTube viewing (resizing layout, Versus three views), voting, Support and wallet, artist setup and the live show, delivery and metering, security, privacy, safety, financial crime, release flow, observability and performance. | Reflects the architecture v2, the user journey, the YouTube decision and the Versus decisions.
Added | PRD tab, new columns J to M | Surface, Build plan phase (v2), Design boards, Change note. | Lets Claude Code cite PRD rows and find the matching boards. Mapping for older rows is proposed: please skim it.
Updated | Rows 15, 16, 17, 19 | Moving zoom and pan are real lens-based settings (Should, Phase 2). Auto director is built and on by default (Must for row 17, Should for row 19). | Decisions of 30 Sept and the built director.
Flagged | Row 10 | Go live at any time conflicts with the 30-minute booking rule. Row not changed; the new Schedule row supersedes it. | Decided 29 Sept.
Flagged | Row 11 | Pre-show recording consent may not be needed: recordings are the product on a contract basis. Left as written. Needs decision. | Architecture privacy table.
Flagged | Rows 54, 61, 62 | Stickers are not in the designs (Support tokens and a reactions tab are). Token purchase is web only and the payment provider is not chosen. | Design and no-payments-in-native rule.
Flagged | Row 50 | Picture quality and buffering are YouTube's under the new delivery model. | YouTube decision.
Updated | Scaling tab | Build plan column and an update note for every existing row; 13 new infrastructure rows (IDs 12 to 24). | Release flow, delivery, stores and backups.
Updated | Legend tab | New Gap Filled? values, new columns and the build plan phases.
Open decision | Viewer-hours | What do viewer-hours mean now that YouTube carries viewers and Loudentify pays no per-viewer media cost? Affects Allowance, packs, metering and pricing. | Architecture v2 risk list.
Open decision | Providers | Payment provider and identity-check provider are not chosen. Build runs against test mode until you decide.
Open decision | Reactions | Reaction design is on hold. Versus reactions need an artist field before they can count for A or B.
Open decision | Picture-in-picture | Embedded YouTube may limit it on native. Decide after real-device testing.
Open decision | Admin console | Admin, support and finance screens are not designed yet. Rows are mapped to Hardening.
Open decision | Google verification | Start now: the live streaming scope needs Google review and default API quota is limited.

## Legend & Notes
Priority (MoSCoW)
Must | Required for the product to be viable at all.
Should | Important, expected soon after core is stable.
Could | Valuable but deferrable without harming core experience.
Won't now | Explicitly out of scope for the foreseeable roadmap; revisit later.
Build Phase
Pilot | This week's minimal live-test build.
Phase 2 | Next build cycle after the pilot validates the format.
Phase 3 | Later refinement, once Phase 2 is stable.
Future Roadmap | Not scheduled; revisit after product-market signal.
Gap Filled? column
'Gap' = story added during review, not in your original draft.
'Duplicate flagged' = overlaps another row; consolidate before finalizing.
'Needs decision' = conflicts with a decision already made elsewhere (e.g. artist sticker bar).
Why some 'Must' rows are still Phase 2, not Pilot
This pilot is deliberately an open layer -- no sign-up, login, or accounts. 'Must' reflects eventual necessity for the product; 'Build Phase' reflects when it's actually needed. Auth, profiles, and admin user-management are Must but Phase 2 for exactly this reason -- confirmed as an explicit decision, not an oversight.
Added 1 October 2026
Gap Filled? values | 'Added 1 Oct' = story added to reflect decisions and the architecture after the original draft. 'Updated 1 Oct' = an existing row changed in place (see Change note). 'Needs decision' = open question; do not build until Korey decides.
New columns | Surface (where it ships), Build plan phase (v2) (which phase of the Claude Code build plan delivers it), Design boards (screens on the canvas), Change note (what changed and why).
Build plan phase (v2)
1 Foundations | Environments and release flow, permission model, audit log, ledger, consent records, data classification, instrumentation.
2 Viewer (web) | Guest preview and sign-up, Discover, Live, search, show screen with YouTube player, Versus views, voting, Support, wallet balance.
3 Artist and live pipeline | Artist onboarding and YouTube connection, scheduling, Kit Check, console, Versus controls, compositor and egress, recordings, clips, earnings.
4 Native apps | iOS and Android apps, camera mode, cloud builds.
5 Website | Public pages, show pages with previews, cookie banner, legal.
6 Hardening | Permission, ledger, load and failure tests, data rights, report queue, assessments, restore drill, admin console, safety.
Post-launch | Not in the first build: competitions, ranking, IP protection, own delivery (loudentify-llhls).
Decision needed | Blocked on a call from Korey. See the Change log tab.
Note | The older Build Phase column (Pilot, Phase 2, Phase 3, Future Roadmap) is kept as written. Every new row is launch scope for the new build, shown as Phase 2.

## Scaling & Infrastructure
Guiding principle
Build on managed, horizontally-scalable infrastructure from day one, so that growth from pilot to 1M+ users is handled by upgrading a subscription tier or plan -- not by re-architecting the application. This is achievable for the pieces listed below. It is NOT the same as claiming zero engineering work is needed later: a few specific code-level decisions (flagged 'Fix now' below) must be made correctly from the start regardless of current traffic, because they are correctness issues that happen to also be scale issues -- deferring them creates real rework, not just a config change.
ID | Infrastructure Area | Decision | Rationale | Priority (MoSCoW) | Build Phase | Scales by upgrade, or needs engineering? | Notes / Risk if deferred | Build plan phase (v2) | Update (1 Oct)
1 | Database | Use a serverless-native Postgres provider (e.g. Neon or Supabase Postgres) -- not a self-managed database server. | This is the single most consequential unmade decision. A DB that requires manual resizing is the most common reason a fast-built app hits a wall. | Must | Pilot | Upgrade by plan tier | Lock this in before more backend prompts assume 'no database yet' -- every new feature (profiles, comments history, competitions) should be designed against the real DB from the start. | 1 Foundations | Decided: Supabase Postgres. Separate staging and production projects (London); the pilot project is frozen and untouched.
2 | Application hosting | Keep all application logic stateless (Vercel serverless functions / Next.js API routes). Never store per-user or per-room state in server memory. | Stateless functions scale horizontally with zero code changes -- this is already how the current pilot build works; the rule is to keep it that way as features are added. | Must | Pilot | Upgrade by plan tier | Watch for this specifically whenever a prompt is tempted to use a simple in-memory variable 'for now' -- that pattern breaks the moment there's more than one server instance. | 1 Foundations | Unchanged. Application stays stateless.
3 | Real-time video/audio | LiveKit Cloud (already chosen). | Per LiveKit's own published limits, LiveKit Cloud scales horizontally to 100,000+ simultaneous participants per session, with higher tiers unlocking higher quotas and Enterprise removing published ceilings. The SFU architecture itself is not the bottleneck. | Must | Pilot | Upgrade by plan tier | No architecture change needed as usage grows -- monitor plan quotas (concurrent rooms, egress minutes) and upgrade tier before hitting them, not after. | 3 Artist and live pipeline | LiveKit stays for ingest, mixing and egress. Viewer fan-out moves to YouTube first, so LiveKit viewer quotas stop being the constraint.
4 | Shared real-time counters (e.g. go-loud threshold) | Move from each client independently summing data messages to an authoritative shared count (server-side, or a shared store like Redis). | This is a correctness issue, not just a scale issue -- the current client-side tally can already double-count or desync with even a moderate number of participants, independent of total platform scale. | Should | Phase 2 | Needs engineering | Fix now conceptually (design the API right) even though the pilot's small room size hides the symptom today. Flagged as a 'Fix now' item. | 3 Artist and live pipeline | Also applies to votes: one authoritative count, stamped with playback position.
5 | Background/async jobs | Add a job queue for anything slow or external: egress recording, notification delivery, share-preview image generation. | Prevents a slow external call from blocking or timing out a user-facing request; keeps the stateless request/response model intact at any volume. | Should | Phase 2 | Needs engineering | Design new features (recording, sharing) to hand off to a background job from the start, rather than doing the work inline and retrofitting later. | 3 Artist and live pipeline | Also: YouTube broadcast lifecycle, metering reconciliation, data export, payout reconciliation.
6 | Rate limiting & abuse protection | Add per-IP and per-user rate limiting middleware on all public API routes. | Cheap to add now; expensive and reactive to add after real abuse patterns emerge at scale. | Should | Phase 2 | Needs engineering | Consider moving this to 'Pilot' phase given how cheap it is -- doesn't need to wait for Phase 2 specifically. | 6 Hardening | Cheap and still pending; do it before the first public show.
7 | CDN & static assets | Rely on Vercel's built-in CDN for static assets; no custom asset-serving path. | Already the default behavior of the current hosting choice -- no action needed unless a future feature bypasses it. | Must | Pilot | Upgrade by plan tier | Just don't build a custom file-serving route that bypasses the CDN for things like profile images or clips. | 5 Website | Unchanged.
8 | Media/file storage | Use S3-compatible object storage for recordings, uploaded backing tracks, and profile/artist images. | Object storage scales independently of the app and database; needed regardless once recording (egress) or backing-track upload (Case 3 audio) is built. | Should | Phase 2 | Upgrade by plan tier | Decide the provider (S3, or Supabase Storage if already using Supabase for DB) before egress or backing-track features are built, so files land in the right place from day one. | 3 Artist and live pipeline | Private object storage, signed URLs, hot 30 days then cold. Provider still to confirm (Supabase Storage or S3).
9 | Authentication | Use a managed auth provider (e.g. Supabase Auth, Clerk, or NextAuth) rather than hand-rolled password/2FA logic. | Authentication security is easy to get subtly wrong when hand-built quickly; managed providers handle password hashing, session security, and 2FA correctly and scale without extra work. | Must | Phase 2 | Upgrade by plan tier | This should be decided before the sign-up/login stories in the main PRD tab are built, not after. | 1 Foundations | Decided direction: Supabase Auth with passkeys and Apple and Google sign-in.
10 | Observability | Add error tracking and logging (Vercel's built-in logs at minimum, plus a dedicated error tracker as usage grows). | At real scale, problems become invisible without this -- and retrofitting observability after an incident is much harder than having it from the start. | Should | Phase 2 | Needs engineering | Even a lightweight version now (structured console logging with request IDs) pays off later. | 1 Foundations | See 'Observability (v2)' below: correlation ids and journey events.
11 | Vendor lock-in awareness | Managed choices above (Vercel, LiveKit Cloud, Neon/Supabase) trade a little lock-in for a lot of scaling ease -- but none of them are dead ends. | LiveKit is open-source and self-hostable if ever needed; Postgres is a portable, standard database engine regardless of provider. This is a reasonable tradeoff, not a trap. | Should | Pilot | Principle, not a build task | Revisit only if a specific limit or cost becomes a real constraint -- don't preemptively avoid managed services out of lock-in fear alone. | 1 Foundations | Reinforced: delivery sits behind PlayerSource so YouTube is not a lock-in.
12 | Environments and release | Local, staging and production on separate Supabase projects, keys and data. Pull request into staging, pipeline applies migrations, promote workflow (human approval) applies the same migrations and deploys to production. | Staging catches mistakes before production; production credentials stay out of reach of the build agent. | Must | Phase 2 | Needs engineering | Production credentials only as GitHub production-environment secrets. Rollback scripts for every migration. | 1 Foundations | New in v2
13 | Live delivery | Viewers watch an embedded YouTube player first. Delivery sits behind a PlayerSource interface with youtube and loudentify-llhls implementations. | Removes per-viewer streaming cost, which was too high to scale. Own delivery returns when funded. | Must | Phase 2 | Upgrade by plan tier | Cannot overlay the player; embed cookies need consent; YouTube availability is outside our control. | 2 Viewer (web) | New in v2
14 | Compositor and egress | Compose one portrait picture (solo or the three Versus views) and send one egress over RTMP to YouTube, plus the recording and training copy. | One composed output keeps cost to one egress per show and keeps artists and viewers on the same picture. | Must | Phase 2 | Needs engineering | Cap concurrent shows per region at launch; compositor compute scales with live shows, not viewers. | 3 Artist and live pipeline | New in v2
15 | YouTube API and Google verification | Create and end broadcasts through the YouTube Live Streaming API using the artist's own connection. | Needed for the whole delivery model. | Must | Phase 2 | Needs engineering | Sensitive scope needs Google verification; default API quota is limited. Start early. | 3 Artist and live pipeline | New in v2
16 | Identity store | Credentials, sessions, passkeys, date of birth and YouTube tokens in a separate schema with separate credentials and per-tenant encryption keys. | A fault in the application store must not expose identity data or tokens. | Must | Phase 2 | Needs engineering | Tokens never returned to a client or logged. | 1 Foundations | New in v2
17 | Money ledger store | Double-entry append-only ledger in its own database with no delete privilege for any application role. | Balances must always be explainable. | Must | Phase 2 | Needs engineering | Money reads from the primary, never a replica. | 1 Foundations | New in v2
18 | Audit log store | Separate account, append-only, hash-chained, queryable without touching application data. | Needs a year of evidence for SOC 2; compromising the app must not rewrite history. | Must | Phase 2 | Needs engineering | Audit write failure is a paging alert. | 1 Foundations | New in v2
19 | Feed read model and caching | Precompute per-viewer feeds; short-lived caches for live state; read replicas for feeds and profiles; cursor pagination. | The difference between a feed that works at a thousand users and at a million. | Should | Phase 2 | Needs engineering | Only one live player instance at a time on the client. | 2 Viewer (web) | New in v2
20 | Analytics store | Behaviour events with pseudonymous ids only, kept outside the main database, 13-month retention. | Keeps hot tables narrow and personal data out of analytics. | Should | Phase 2 | Needs engineering | No names, emails or message contents. | 1 Foundations | New in v2
21 | Backups and recovery | Point-in-time recovery with 5-minute RPO and 1-hour RTO, encrypted backups in a separate account, restored in a test every quarter. | An untested backup is a guess. | Must | Phase 2 | Upgrade by plan tier | Free-tier Supabase projects lack this: production needs a paid plan before real users. | 6 Hardening | New in v2
22 | Secrets and code scanning | Secrets manager, secret scanning with push protection, dependency and container scanning in the pipeline. | A leaked key does not announce itself. | Must | Phase 2 | Needs engineering | The build agent never sees production secrets. | 1 Foundations | New in v2
23 | Observability (v2) | Correlation id on every request; journey events; per-show camera, audio, egress and YouTube metrics; alerts only for a few things. | Instrumentation lets us react during a show. | Must | Phase 2 | Needs engineering | Replaces the lighter version in the Observability row above. | 1 Foundations | New in v2
24 | Cost tracking | Track cost per show-hour (egress, compute, storage) and YouTube quota use from the first show. | Pricing depends on knowing it; viewer-hours no longer carry a media cost. | Should | Phase 2 | Needs engineering | Decision needed on what viewer-hours mean. | 3 Artist and live pipeline | New in v2